## Sheet1
Event Critical Timeline
Time Frame | Item | Sub Item | Who
12 Months Out | Events Purpose
Survey Board
Survey Sponsors
Assign Event Lead/Point Person
Start deveoping event budget
Research Event Date
Create Venue RFP
Determine Event Committee
Host Committee
Working Committee
Honorary Committee
Silent Auction
Table Sales
Marketing
Voluntees
Research Honorees/VIP's
11 Months Out
Collect Venue RFP's
Select Event Date
Develop Sponsorship Materials
Gather ideas for Enterainment
Work on Marketing Strategy
Website
Ticketing
Print/Media
Work on dividing up assignements/duties
Entertainment Needs
Menus
Permits
Signage
Contracts
Develop Auction Asks/Lists
6 Months Out
Develop Printed Materials
Social Media Plan
Site Visits
Lock in Vendors
Create Volunteer Needs
Secure Acution Items
Secure Sponsors
Logos
Confirm Final Budget Numbers
3 Months Out
Compose Invitation Lists
Finalize Menu
Vendor Walk Through
Finalize Décor
Complete Signage List
Finalize Site Plans
Work on Program
Run of Show
Script
2 Months Out
Send Invitations
Start Recruiting Volunters
Gather up auciton items
Confirm Speakers/VIP Tralve
Vendor Deposits
1 Month Out
Finalize All Layouts/Diagrams
Send Out Printed Materials
Signage
Step and Repeat
Program/Menu
Schedule Final Walk Through
Finalize Load In Schedule
Order Invoices/Checks
Send Final Scripts
Arrange for rehearsal
Final Vendor Walk Through
Confirm Volunteers
Create Production Timeline
Send One Sheets
Guests
Staff
Volunteers
VIPs
Receive Printed Materials
2 Days Prior
Print Name Badges
Print Guest Lists
Stuff Event Bags/Packets
Review Timeline with Staff
Confirm Event Pack
Print Timelines
Day of
Arrive Early
Set up produciton Office
Check All Areas
Confirm Vendors as they arrive
Check off production timeline
Final Vendor Payments
Registration Lists (updates)
Review Timeline with Staff (yes again)
Meet with Catering/Review Timing
Do a rehearsal
Check all AV
Video
Sound
Lighting
Post Event
Thank you notes
Ensure all invoices paid
Post Mortum Meeting
Vendors
Staff
Follow up meetings